Capstone Project Work Plan: AI Integration in Business Practices

Objective: To research, design, and propose an AI integration model tailored to improve business practices, demonstrating feasibility, scalability, and impact.

Semester Timeline:

Phase 1: Project Planning and Research (Weeks 1-2)

- Define Goals:

  - Clarify project scope, deliverables, and evaluation criteria.

  - Consult with advisor and stakeholders for input and expectations.

- Literature Review:

  - Analyze existing AI applications in various industries.

  - Identify trends, challenges, and opportunities in AI-driven business transformations.

- Select Business Domain:

  - Choose a specific industry or business process to focus on (e.g., supply chain, customer service, or marketing).

- Develop Research Questions:

  - What business problems can AI address effectively?

  - How does AI implementation impact efficiency, cost, and decision-making?

Deliverables: Project proposal and literature review summary.

Phase 2: Data Collection and Analysis (Weeks 3-5)

- Identify Data Needs:

  - Determine data requirements for analysis and modeling.

  - Assess the availability and quality of relevant data sources.

- Collect Data:

  - Gather data from selected business processes or publicly available datasets.

  - Collaborate with businesses or use simulation data if required.

- Analyze Data:

  - Use statistical tools to identify patterns and insights.

  - Highlight inefficiencies and potential areas for AI application.

Deliverables: Data collection report and preliminary analysis.

Phase 3: AI Model Design and Development (Weeks 6-9)

- Define AI Solution:

  - Select appropriate AI techniques (e.g., machine learning, natural language processing).

  - Align model design with identified business goals.

- Prototype Development:

  - Build a prototype AI model.

  - Test functionality and make iterative improvements.

- Validate Solution:

  - Evaluate model performance using key metrics (e.g., accuracy, efficiency).

  - Seek feedback from advisors or industry mentors.

Deliverables: Prototype and validation report.

Phase 4: Implementation Framework and Testing (Weeks 10-11)

- Develop Implementation Plan:

  - Create a step-by-step guide for integrating the AI solution into business processes.

  - Address potential challenges and propose mitigation strategies.

- Simulation Testing:

  - Simulate AI deployment in a controlled environment.

  - Assess performance and potential real-world impacts.

Deliverables: Implementation framework and simulation results.

Phase 5: Finalization and Presentation (Week 12)

- Document Findings:

  - Compile all research, analysis, and design into a comprehensive report.

  - Highlight key insights, solution feasibility, and projected outcomes.

- Prepare Presentation:

  - Create a visual and engaging presentation for project stakeholders.

  - Practice delivery and incorporate feedback.

- Submit Deliverables:

  - Turn in final report and presentation materials.

Deliverables: Final report, presentation slides, and any supplementary materials.

Tools and Resources:

- Software: Python (AI modeling), Tableau/Power BI (data visualization), Jupyter Notebook.

- Research Databases: IEEE Xplore, Google Scholar, industry whitepapers.

- Communication: Regular advisor check-ins and peer reviews.

Evaluation Metrics:

- Depth of research and analysis.

- Innovation and practicality of the proposed AI solution.

- Clarity and professionalism of deliverables.

- Feedback from advisors and stakeholders.

Contingency Plan:

- Address potential risks such as data unavailability or technical challenges by having backup datasets or alternative AI techniques.

- Allow buffer time for unexpected delays during prototyping and testing.